## Summary
Client | Lilly China
Project Code | PLC219
Project Name | LCCP 2020
Project Manager | Christina Deng
As at 23-Aug-20 |  | Cost
Budget |  | 1128960
Target | 90% | 1016064
Actual Costs (AC) | 49.16% | 555005
Estimate To Completion (ETC) | 28.68% | 323800
Estimate At Completion (EAC = AC + ETC) | 77.84% | 878805

## Cost
Name | Role | Rate | Costs |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
|  |  | Spent | Remaining | Total | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21
Christina Deng | Sr. Business Analyst | 120 | 72060 | 43200 | 115260 | 1920 | 2400 | 2880 | 1920 |  |  | 2400 | 2400 | 2400 | 2400 | 2640 | 2400 | 2400 | 2160 | 1920 | 2160 | 2880 | 1920 | 1440 | 1920 | 2400 | 2400 | 2400 | 2520 | 1440 | 1920 | 1560 | 3120 | 2400 | 2280 | 2340 | 2280 | 2160 | 2280 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
Eva Wang | Designer | 120 | 15600 |  | 15600 | Wk 2: 1080; Wk 3: 780; Wk 4: 300; Wk 7: 120; Wk 8: 300; Wk 9: 2820; Wk 10: 840; Wk 11: 120; Wk 12: 540; Wk 13: 2760; Wk 14: 1080; Wk 15: 240; Wk 16: 960; Wk 17: 60; Wk 20: 180; Wk 21: 60; Wk 23: 1020; Wk 24: 2340
Floria Sui | Developer | 80 | 14840 | 1600 | 16440 | Wk 2: 1840; Wk 3: 1360; Wk 18: 640; Wk 28: 1600; Wk 29: 1600; Wk 30: 1400; Wk 31: 1600; Wk 32: 1600; Wk 33: 1600; Wk 34: 1600; Wk 35: 1600
Hellen Ni | Jr. Developer | 70 | 44520 | 25200 | 69720 | 560 | 2590 | 1120 |  |  |  | 1400 | 1890 | 1400 | 1680 | 1400 | 1400 | 1680 | 1120 | 1120 | 1400 | 1960 | 840 | 1120 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1120 | 1400 | 1120 | 1400 | 1400 | 1400 | 1400 | 1400 | 2800 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
Henry He | Solution Architect | 240 | 83280 | 43200 | 126480 | 1920 | 6240 | 5040 | 2160 |  |  | 1440 | 2400 | 3360 | 2400 | 2880 | 960 | 4320 | 8640 | 3840 | 5520 | 6960 | 4320 | 1680 | 720 | 1680 | 240 | 1440 |  |  | 960 | 1920 | 2640 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
Jie Tian | Sr. Project Manager | 230 | 24840 | 41400 | 66240 | [16 empty] | 920 | 230 | 230 |  |  |  |  | 4370 | 2300 | 1610 | 1840 | 2070 | 460 | 2300 | 2300 | 2300 | 1840 | 2070 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300
Joyce Liu | User Researcher | 150 | 9225 |  | 9225 | Wk 1: 150; Wk 2: 1500; Wk 3: 900; Wk 4: 150; Wk 9: 1500; Wk 10: 300; Wk 11: 450; Wk 13: 600; Wk 14: 150; Wk 16: 150; Wk 17: 525; Wk 18: 750; Wk 19: 450; Wk 20: 450; Wk 21: 1200
Larry Sun | Designer | 120 | 1320 |  | 1320 | Wk 9: 240; Wk 17: 1080
Leon Ren | Software Technical Lead | 150 | 107850 | 54000 | 161850 | 1200 | 450 | 2400 | 1650 |  |  | 900 | 2550 | 4275 | 3300 | 5250 | 6825 | 2700 | 1050 | 2400 | 5100 | 7050 | 3300 | 4050 | 6000 | 5700 | 5550 | 2400 | 1500 | 1650 | 3150 | 5250 | 1800 | 4350 | 3150 | 2550 | 4350 | 3150 | 2850 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
Vicky Li | Sr. QA Analyst | 120 | 68040 | 43200 | 111240 | 960 | 480 |  | 960 |  |  | 2400 | 4440 | 2400 | 2400 | 1440 | 1440 | 3840 | 2400 | 1440 | 2400 | 2880 | 1920 | 1920 | 2400 | 2400 | 2400 | 2400 | 2400 | 1920 | 1200 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
Yang Song | Software Engineer | 100 | 113430 | 72000 | 185430 | 1600 | 4000 | 3500 | 3200 |  |  | 4800 | 4000 | 4000 | 4000 | 4200 | 4800 | 4000 | 4000 | 4000 | 4000 | 4800 | 3200 | 3200 | 4000 | 4000 | 4000 | 4130 | 4000 |  |  |  | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  |  | 555005 | 323800 | 878805 | 8310 | 20580 | 17980 | 10340 | 0 | 0 | 13460 | 17980 | 22395 | 17320 | 18380 | 18365 | 22300 | 20600 | 14960 | 21690 | 29115 | 17120 | 14090 | 17070 | 18840 | 15990 | 15190 | 18530 | 8710 | 9960 | 14370 | 18750 | 18530 | 18850 | 18510 | 20250 | 18470 | 18000 | 19500 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900 | 17900
Legend
Spent (Costs)
[6 empty] | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Hours
Name | Role | Hours |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
|  | Spent | Remaining | Total | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21
Christina Deng | Sr. Business Analyst | 600.5 | 360 | 960.5 | 16 | 20 | 24 | 16 |  |  | 20 | 20 | 20 | 20 | 22 | 20 | 20 | 18 | 16 | 18 | 24 | 16 | 12 | 16 | 20 | 20 | 20 | 21 | 12 | 16 | 13 | 26 | 20 | 19 | 19.5 | 19 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Eva Wang | Designer | 130 |  | 130 | Wk 2: 9; Wk 3: 6.5; Wk 4: 2.5; Wk 7: 1; Wk 8: 2.5; Wk 9: 23.5; Wk 10: 7; Wk 11: 1; Wk 12: 4.5; Wk 13: 23; Wk 14: 9; Wk 15: 2; Wk 16: 8; Wk 17: 0.5; Wk 20: 1.5; Wk 21: 0.5; Wk 23: 8.5; Wk 24: 19.5
Floria Sui | Developer | 185.5 | 20 | 205.5 | Wk 2: 23; Wk 3: 17; Wk 18: 8; Wk 28: 20; Wk 29: 20; Wk 30: 17.5; Wk 31: 20; Wk 32: 20; Wk 33: 20; Wk 34: 20; Wk 35: 20
Hellen Ni | Jr. Developer | 636 | 360 | 996 | 8 | 37 | 16 |  |  |  | 20 | 27 | 20 | 24 | 20 | 20 | 24 | 16 | 16 | 20 | 28 | 12 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 20 | 16 | 20 | 20 | 20 | 20 | 20 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Henry He | Solution Architect | 347 | 180 | 527 | 8 | 26 | 21 | 9 |  |  | 6 | 10 | 14 | 10 | 12 | 4 | 18 | 36 | 16 | 23 | 29 | 18 | 7 | 3 | 7 | 1 | 6 |  |  | 4 | 8 | 11 | 8 | 8 | 8 | 8 | 8 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Jie Tian | Sr. Project Manager | 108 | 180 | 288 | [16 empty] | 4 | 1 | 1 |  |  |  |  | 19 | 10 | 7 | 8 | 9 | 2 | 10 | 10 | 10 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Joyce Liu | User Researcher | 61.5 |  | 61.5 | Wk 1: 1; Wk 2: 10; Wk 3: 6; Wk 4: 1; Wk 9: 10; Wk 10: 2; Wk 11: 3; Wk 13: 4; Wk 14: 1; Wk 16: 1; Wk 17: 3.5; Wk 18: 5; Wk 19: 3; Wk 20: 3; Wk 21: 8
Larry Sun | Designer | 11 |  | 11 | Wk 9: 2; Wk 17: 9
Leon Ren | Software Technical Lead | 719 | 360 | 1079 | 8 | 3 | 16 | 11 |  |  | 6 | 17 | 28.5 | 22 | 35 | 45.5 | 18 | 7 | 16 | 34 | 47 | 22 | 27 | 40 | 38 | 37 | 16 | 10 | 11 | 21 | 35 | 12 | 29 | 21 | 17 | 29 | 21 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Vicky Li | Sr. QA Analyst | 567 | 360 | 927 | 8 | 4 |  | 8 |  |  | 20 | 37 | 20 | 20 | 12 | 12 | 32 | 20 | 12 | 20 | 24 | 16 | 16 | 20 | 20 | 20 | 20 | 20 | 16 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Yang Song | Software Engineer | 1134.3 | 720 | 1854.3 | 16 | 40 | 35 | 32 |  |  | 48 | 40 | 40 | 40 | 42 | 48 | 40 | 40 | 40 | 40 | 48 | 32 | 32 | 40 | 40 | 40 | 41.3 | 40 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Total |  | 4499.8 | 2540 | 7039.8 | 65 | 172 | 141.5 | 79.5 | 0 | 0 | 121 | 153.5 | 178 | 145 | 147 | 154 | 179 | 147 | 118 | 164 | 217 | 130 | 114 | 143.5 | 153.5 | 138 | 131.8 | 149.5 | 69 | 74 | 104 | 154 | 159 | 155.5 | 154.5 | 166 | 155 | 167 | 160 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
Legend
Spent (Hours)
Current Week
[5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2020-08-23
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done

## Budget
WO# | Comments | Role | Months | Hours | Cost | Comments2 | Role | 医生端
|  | Project Manager | 6 | 960 | 201600
|  | Solution Architect | 6 | 960 | 230400 |  | Project Manager | 0.5
|  | Sr. Programmer | 18 | 2880 | 374400 |  | Sr. Business Analyst | 0
|  | Programmer | 6 | 960 | 96000 |  | Solution Architect | 0.5
|  | Data Consultant | 6 | 960 | 144000 |  | Sr. Programmer | 1.5
|  | Sr. Quality Assurance | 3 | 480 | 57600 |  | Programmer | 0.5
|  | Graphic Design/Interaction Design | 1.3 | 208 | 24960 | 实报实销 | Sr. Quality Assurance | 0.5
[7 empty] | Data Consultant | 0.5
[7 empty] | Design(平均) | 实报实销
[7 empty] | 总计 （man） | 4
Budget至2020年年底
|  | Total | 46.3 | 7408 | 1128960

## Rate Card
Function | External Role | External Factor | Function | Internal Role | Internal Factor
Business | Information Consultant | 270 | Business | Account Manager | 270
Business | Innovation Analyst | 240 | Business | Sr. Business Consultant | 240
Business | Sr. Business Analyst | 120 | Business | Sr. Business Analyst | 120
Business | Business Analyst | 100 | Business | Business Analyst | 100
Creative | Art/Creation Direction | 350 | Creative | Head of Design | 350
Creative | User Researcher | 170 | Creative | Experience Design Lead | 200
Creative | Copywriter | 120 | Creative | Sr. User Researcher | 170
Creative | Graphic Design/Interaction Design | 120 | Creative | Sr. Copywriter | 150
Data | Data Architect | 240 | Creative | Sr. Designer | 150
Data | Data Consultant | 150 | Creative | User Researcher | 150
Project Management | Data Project Manager | 270 | Creative | Copywriter | 120
Project Management | Sr. Project Manager | 230 | Creative | Designer | 120
Project Management | Project Manager | 210 | Data | Sr. Data Consultant | 270
Project Management | Project Coordinator | 100 | Data | Data Consultant | 240
Quality | Sr. Quality Assurance | 120 | Data | Assoc. Data Consultant | 170
Quality | Quality Assurance | 100 | Data | Data Technical Lead | 150
SQA | SQA Manager | 240 | Data | Sr. Data Specialist | 130
SQA | SQA | 100 | Data | Data Specialist | 100
Technical | Solution Architect (Node.js) | 270 | Others | Intern | 30
Technical | Solution Architect | 240 | Project Management | Sr. Project Manager | 230
Technical | Sr. Mobile Developer | 150 | Project Management | Project Manager | 210
Technical | Sr. Systems Analyst | 150 | Project Management | Assoc. Project Manager | 170
Technical | Mobile Developer | 130 | Project Management | Project Lead | 120
Technical | Sr. Programmer | 130 | Project Management | Sr. Project Coordinator | 100
Technical | Systems Analyst | 130 | Project Management | Project Coordinator | 80
Technical | Programmer | 100 | Quality | QA Lead | 150
|  |  | Quality | Sr. QA Analyst | 120
|  |  | Quality | QA Analyst | 100
|  |  | Quality | Software Tester | 70
|  |  | Quality | Jr. Software Tester | 50
|  |  | SQA | SQA Manager | 240
|  |  | SQA | SQA Executive | 100
|  |  | Technical | Sr. Solution Architect | 270
|  |  | Technical | Solution Architect | 240
|  |  | Technical | Assoc. Solution Architect | 220
|  |  | Technical | Software Technical Lead | 150
|  |  | Technical | Sr. Software Engineer | 130
|  |  | Technical | Software Engineer | 100
|  |  | Technical | Developer | 80
|  |  | Technical | Jr. Developer | 70

## Staff
Name | Title
_Business Analyst | Business Analyst
_Designer | Designer
_QA Analyst | QA Analyst
_Software Engineer | Software Engineer
_Solution Architect | Solution Architect
_Sr. Business Analyst | Sr. Business Analyst
_Sr. QA Analyst | Sr. QA Analyst
_Sr. Software Engineer | Sr. Software Engineer
Aaron SHUMAKER | Account Manager
Adam CHUA | Sr. Designer
Adis SUN | Sr. Software Engineer
Albert ZHANG | Software Engineer
Alkaid DING | Developer
Andy CUI | Project Manager
Ao ZHANG | Intern
Baihui LIU | Jr. Developer
Bin YU | Software Engineer
Brian WANG | Jr. Developer
Caler ZHAO | Developer
Candice WANG | Developer
Celestine SHAW | Intern
Chao YANG | Project Coordinator
Charles LI | Assoc. Data Consultant
Chendong XIE | Software Engineer
Chenyang ZHAO | Software Engineer
Chris CHEN | Business Analyst
Christina DENG | Sr. Business Analyst
Christopher Wong | Project Manager
Chuang YU | Sr. Data Specialist
Chunliang SONG | Intern
Cindy Zhang | Jr. Developer
Claire GAO | Sr. QA Analyst
Coca PAN | Jr. Developer
Crystal ZHENG | Project Coordinator
Cynthia CHEN | Intern
Daming YIN | Data Technical Lead
David LI | Account Manager
Dong LIANG | Intern
Dylan HUANG | Software Engineer
Edwin JI | Project Manager
Elaine YANG | QA Analyst
Eric YU | Intern
Ethan MA | Sr. Software Engineer
Eva WANG | Designer
Falcon WANG | Software Technical Lead
Floria SUI | Developer
Frank CAI | Developer
Gavin SUN | Sr. Software Engineer
Gerard CHEN | Software Technical Lead
Guang XIN | Sr. Software Engineer
Guangzhong WANG | Software Engineer
Haibao FENG | Software Engineer
Haining LI | Assoc. Project Manager
Hang CHEN | Jr. Developer
Hank HAN | Project Manager
He WANG | Jr. Developer
Hedy HOU | SQA Manager
Hellen NI | Jr. Developer
Henry CONG | Assoc. Data Consultant
Henry HE | Solution Architect
Honghong LI | Data Technical Lead
Hongming ZHANG | Intern
Huichao LIU | Sr. Software Engineer
Huijun SUN | QA Analyst
Jane ZHANG | SQA
Jayson ONG | Experience Design Lead
Jeff JIN | Solution Architect
Jeffrey CUELLAR | Sr. Copywriter
Jessica GAO | Account Manager
Jessie LIU | Intern
Jian LIANG | Data Technical Lead
Jian ZHU | Sr. Business Consultant
Jianan LI | Sr. Software Engineer
Jiaxiang WANG | Sr. Software Engineer
Jie TIAN | Sr. Project Manager
Jingbin LI | Intern
Joanna JI | QA Analyst
Joe Zou | IT Supervisor
John TAN | Project Manager
John XIE | Assoc. Solution Architect
Johnny YU | Business Analyst
Johnson ZHONG | Sr. Solution Architect
Joyce LIU | User Researcher
Juan BAI | Intern
Jupei LU | Intern
Karthik RAMASWAMY | Sr. Solution Architect
Katharina MA | Intern
Kent SUN | Software Engineer
Kilin LEE | Sr. Software Engineer
Larry SUN | Designer
Leon REN | Software Technical Lead
Link YANG | Solution Architect
Lisa LI | Sr. QA Analyst
Liya MENG | Jr. Developer
Liye SHI | Sr. Data Specialist
Lucy ZHENG | Software Engineer
Manchao LI | Developer
Marvin CUI | Software Engineer
Mary YAN | Business Analyst
Mary YUAN | Intern
Matthew ELSOM | Head of Design
May YANG | Sr. Software Engineer
Meiyi LI | Jr. Developer
Meiying LI | Jr. Developer
Messi CONG | Sr. Software Engineer
Mona LI | Intern
Monica YANG | Assoc. Project Manager
Nanming ZHAO | Sr. Data Specialist
Ni LI | QA Analyst
Nick WU | Sr. Software Engineer
Nicole LI | Business Analyst
Ning LI | Software Technical Lead
Olivia HUI | Business Analyst
Oscar SHU | Developer
Peng WANG | Intern
Polina PENG | Software Tester
Qi ZHANG | Jr. Developer
Qingshen KONG | Jr. Developer
Qiu LI | Developer
Quintina MEI | QA Analyst
Rentao XIAO | Sr. Software Engineer
Renzhang PAN | Intern
Ronglei HU | Intern
Sandy WANG | Project Lead
Shaoyu WANG | Jr. Developer
Shenglin JIN | Intern
Shin GAO | Software Engineer
Shishuai LIU | Jr. Developer
Shuai PANG | Jr. Developer
Shuai ZHOU | Sr. Project Manager
Simon HU | Software Technical Lead
Spring ZHANG | Developer
Stevens ZHOU | Designer
Summer ZHANG | Sr. Project Coordinator
Sunny NAN | QA Analyst
Sylvia HAN | QA Analyst
Tingchong LIU | Project Manager
Tiny CHEN | Business Analyst
Tom LIU | Software Engineer
Vicky LI | Sr. QA Analyst
Vicky ZHU | Sr. Business Analyst
Vincent HUANG | Sr. User Researcher
Vivian DU | Software Engineer
Wencan LIU | Jr. Developer
Wenyu WANG | QA Analyst
White BAI | Software Engineer
Will BI | Software Technical Lead
Xian TANG | Software Engineer
Xiaoning GUO | Software Technical Lead
Xiaoshi SHEN | Jr. Developer
Xinfeng LIU | Intern
Xinning CHIA | Designer
Xu MA | QA Analyst
Yan LI | Intern
Yang CHEN | QA Analyst
Yang SONG | Software Engineer
Yang YANG | Data Technical Lead
Yantao LIU | Software Engineer
Yici ZHONG | QA Analyst
Yifeng LIU | Intern
Yihe SUN | Intern
Yingjun LIU | Sr. Project Manager
Yue LI | Intern
Yuhua LI | Sr. Software Engineer
Yupeng CHEN | Intern
Zhaojiang PEI | Intern
Zhen WU | Intern
Zheng LI | Sr. Software Engineer
Zhikang ZENG | Jr. Developer
Zoi CHU | QA Analyst
Zora DONG | Intern
Kermy MU | Business Analyst
Dave GAO | Software Engineer