## Summary
Client | LillyChina Medical |  | 说明：
Project Code | PLC227.X |  | PM需要填写绿色填充部分； PM在项目申请立项时填写此表格，发送Business Support，并保存到Sharepoint中。 更新：如有变更，PM需要及时调整Resource Plan，每周与周报同步update。 路径：sharepoint 中 Project Manage Group中。
Project Name | LCDDMAC Portal
Project Manager | Jie TIAN
As at 02-Aug-20 |  | Cost | Cost | 计算方法 | 填写方法
Budget |  | 61600 | C7 | 数据来源于【Budget】 | PM按照项目Estimation，【Budget】进行填写；
Target | 90% | 55440 | C8 | Budget * Target 百分比 | DM input给PM本项目的目标值，如果PM不清晰需要与DM明确。 通常情况为80%，根据项目的难易程度、人员情况等进行调整。
Actual Costs (AC) | 12.72% | 7835 | C9 | 数据来源于【Cost】Spent Total | PM按照Estimation和实际投入，【Hours】进行人员工时分配； PM按照实际Tracking【Hours】check ‘Done’。
Estimate To Completion (ETC) | 66.4% | 40900 | C10 | 数据来源于【Cost】Remaining Total | PM不需填写，工具根据【Hours】check ‘Done’情况自动计算
Estimate At Completion (EAC = AC + ETC) | 79.12% | 48735 | C11 | 数据来源于【Summary】C9+C10 | PM不需要填写，工具自动计算； 计算B11 EAC百分比，PM根据预估情况采取改善措施。 （EAC<Target 为绿色，如有超出变成黄色或红色）
Milestone | Start Date | End Date
Duration | 2020-05-01 | 2020-05-30
Kick off | 2020-05-02 | -
Requirement Develop | 2020-05-02 | 2020-05-05
Requirement sign off | 2020-05-10 | -
Develop | 2020-05-06 | 2020-05-20
SIT | 2020-05-20 | 2020-05-25
UAT | 2020-05-25 | 2020-05-28
PRD | 2020-05-29 | -

## Cost
Name | Role | Rate | Costs |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
|  |  | Spent | Remaining | Total | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17
Jie TIAN | Sr. Project Manager | 230 | 3335 | 9200 | 12535 | Wk 8: 1725; Wk 9: 1150; Wk 10: 460; Wk 11: 1840; Wk 12: 1840; Wk 13: 1840; Wk 14: 1840; Wk 15: 1840
Simon HU | Software Technical Lead | 150 |  | 7500 | 7500 | Wk 11: 1500; Wk 12: 1500; Wk 13: 1500; Wk 14: 1500; Wk 15: 1500
Eva Wang | Designer | 120 | 2580 | 1800 | 4380 | Wk 8: 1980; Wk 9: 600; Wk 11: 1200; Wk 12: 600
Zora DONG | Intern | 30 |  | 2400 | 2400 | Wk 12: 600; Wk 13: 600; Wk 14: 600; Wk 15: 600
Mary YAN | Business Analyst | 100 |  | 4000 | 4000 | Wk 11: 800; Wk 12: 800; Wk 13: 800; Wk 14: 800; Wk 15: 800
Floria SUI | Developer | 80 |  | 8000 | 8000 | Wk 11: 1600; Wk 12: 1600; Wk 13: 1600; Wk 14: 1600; Wk 15: 1600
Hongnan Gao | Developer | 80 | 1920 | 8000 | 9920 | Wk 9: 1920; Wk 11: 1600; Wk 12: 1600; Wk 13: 1600; Wk 14: 1600; Wk 15: 1600
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  |  | 7835 | 40900 | 48735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705 | 3670 | 460 | 8540 | 8540 | 7940 | 7940 | 7940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend
Spent (Costs)
[6 empty] | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Hours
Name | Role | Hours |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
|  | Spent | Remaining | Total | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17
Jie TIAN | Sr. Project Manager | 14.5 | 40 | 54.5 | Wk 8: 7.5; Wk 9: 5; Wk 10: 2; Wk 11: 8; Wk 12: 8; Wk 13: 8; Wk 14: 8; Wk 15: 8
Simon HU | Software Technical Lead |  | 50 | 50 | Wk 11: 10; Wk 12: 10; Wk 13: 10; Wk 14: 10; Wk 15: 10
Eva Wang | Designer | 21.5 | 15 | 36.5 | Wk 8: 16.5; Wk 9: 5; Wk 11: 10; Wk 12: 5
Zora DONG | Intern |  | 80 | 80 | Wk 12: 20; Wk 13: 20; Wk 14: 20; Wk 15: 20
Mary YAN | Business Analyst |  | 40 | 40 | Wk 11: 8; Wk 12: 8; Wk 13: 8; Wk 14: 8; Wk 15: 8
Floria SUI | Developer |  | 100 | 100 | Wk 11: 20; Wk 12: 20; Wk 13: 20; Wk 14: 20; Wk 15: 20
Hongnan Gao | Developer | 24 | 100 | 124 | Wk 9: 24; Wk 11: 20; Wk 12: 20; Wk 13: 20; Wk 14: 20; Wk 15: 20
Total |  | 60 | 425 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 34 | 2 | 76 | 91 | 86 | 86 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend
Spent (Hours)
Current Week
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2020-08-02
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done

## Budget
WO# | Comments | Role | Months | Hours | Cost
|  | Sr. Project Manager | 0.28 | 44.8 | 10304
|  | Graphic Design/Interaction Design | 0.75 | 120 | 14400
|  | Sr. Programmer | 0.7 | 112 | 14560
|  | Programmer | 0.7 | 112 | 11200
|  | Data Consultant | 0 | 0 | 0
|  | Sr. Business Analyst | 0.3 | 48 | 5760
|  | Sr. Quality Assurance | 0.28 | 44.8 | 5376
|  | Total | 3.01 | 481.6 | 61600

## Rate Card
Function | External Role | External Factor | Function | Internal Role | Internal Factor
Business | Information Consultant | 270 | Business | Account Manager | 270
Business | Innovation Analyst | 240 | Business | Business Analyst | 100
Business | Sr. Business Analyst | 120 | Business | Sr. Business Analyst | 120
Business | Business Analyst | 100 | Business | Sr. Business Consultant | 240
Creative | Art/Creation Direction | 350 | Creative | Copywriter | 120
Creative | User Researcher | 170 | Creative | Designer | 120
Creative | Copywriter | 120 | Creative | Experience Design Lead | 200
Creative | Graphic Design/Interaction Design | 120 | Creative | Head of Design | 350
Data | Data Architect | 240 | Creative | Sr. Copywriter | 150
Data | Data Consultant | 150 | Creative | Sr. Designer | 150
Project Management | Data Project Manager | 270 | Creative | Sr. User Researcher | 170
Project Management | Sr. Project Manager | 230 | Creative | User Researcher | 150
Project Management | Project Manager | 210 | Data | Assoc. Data Consultant | 170
Project Management | Project Coordinator | 100 | Data | Data Consultant | 240
Quality | Sr. Quality Assurance | 120 | Data | Data Specialist | 100
Quality | Quality Assurance | 100 | Data | Data Technical Lead | 150
SQA | SQA Manager | 240 | Data | Sr. Data Consultant | 270
SQA | SQA | 100 | Data | Sr. Data Specialist | 130
Technical | Solution Architect (Node.js) | 270 | Others | Intern | 30
Technical | Solution Architect | 240 | Others | Intern - no cost | 0
Technical | Sr. Mobile Developer | 150 | Project Management | Assoc. Project Manager | 170
Technical | Sr. Systems Analyst | 150 | Project Management | Project Coordinator | 80
Technical | Mobile Developer | 130 | Project Management | Project Lead | 120
Technical | Sr. Programmer | 130 | Project Management | Project Manager | 210
Technical | Systems Analyst | 130 | Project Management | Sr. Project Coordinator | 100
Technical | Programmer | 100 | Project Management | Sr. Project Manager | 230
|  |  | Quality | Jr. Software Tester | 50
|  |  | Quality | QA Analyst | 100
|  |  | Quality | QA Lead | 150
|  |  | Quality | Software Tester | 70
|  |  | Quality | Sr. QA Analyst | 120
|  |  | SQA | SQA Executive | 100
|  |  | SQA | SQA Manager | 240
|  |  | Technical | Assoc. Solution Architect | 220
|  |  | Technical | Developer | 80
|  |  | Technical | Jr. Developer | 70
|  |  | Technical | Software Engineer | 100
|  |  | Technical | Software Technical Lead | 150
|  |  | Technical | Solution Architect | 240
|  |  | Technical | Sr. Software Engineer | 130
|  |  | Technical | Sr. Solution Architect | 270

## Staff
Name | Title | Check
_Business Analyst | Business Analyst | 2
_Designer | Designer | 6
_QA Analyst | QA Analyst | 28
_Software Engineer | Software Engineer | 37
_Solution Architect | Solution Architect | 39
_Sr. Business Analyst | Sr. Business Analyst | 3
_Sr. QA Analyst | Sr. QA Analyst | 31
_Sr. Software Engineer | Sr. Software Engineer | 40
Aaron SHUMAKER | Account Manager | 1
Adis SUN | Sr. Software Engineer | 40
Albert ZHANG | Software Engineer | 37
Alkaid DING | Developer | 35
Andy CUI | Project Manager | 24
Ao ZHANG | Intern | 19
Baihui LIU | Jr. Developer | 36
Bin YU | Software Engineer | 37
Burgess LI | Intern | 19
Celestine SHAW | Designer | 6
Charles LI | Assoc. Data Consultant | 13
Chee Kiang CHAN | Designer | 6
Chris CHEN | Business Analyst | 2
Christina DENG | Sr. Business Analyst | 3
Chuang YU | Sr. Data Specialist | 18
Chunliang SONG | Intern | 19
Coca PAN | Jr. Developer | 36
Crystal ZHENG | Project Coordinator | 22
Daming YIN | Data Technical Lead | 16
David LI | Account Manager | 1
Dong LIANG | Intern | 19
Dylan HUANG | Software Engineer | 37
Ethan MA | Sr. Software Engineer | 40
Eva WANG | Designer | 6
Fisher WOON | Software Engineer | 37
Floria SUI | Developer | 35
Frank CAI | Developer | 35
Galvin YEO | Sr. Business Consultant | 4
Gavin SUN | Sr. Software Engineer | 40
Gerard CHEN | Software Technical Lead | 38
Grace WANG | Project Coordinator | 22
Guang XIN | Sr. Software Engineer | 40
Haibao FENG | Software Engineer | 37
Haining LI | Assoc. Project Manager | 21
Hang CHEN | Jr. Developer | 36
Hank HAN | Project Manager | 24
Haorong WANG | Developer | 35
Hedy HOU | SQA Manager | 33
Hellen NI | Jr. Developer | 36
Henry CONG | Assoc. Data Consultant | 13
Henry HE | Solution Architect | 39
Honghong LI | Data Technical Lead | 16
Hongming ZHANG | Intern | 19
Huichao LIU | Sr. Software Engineer | 40
Huijun SUN | QA Analyst | 28
Jane ZHANG | SQA Executive | 32
Jason LEE | Designer | 6
Jayson ONG | Experience Design Lead | 7
Jeff CUELLAR | Sr. Copywriter | 9
Jeff JIN | Solution Architect | 39
Jessie LIU | Intern | 19
Jian LIANG | Data Technical Lead | 16
Jian ZHU | Sr. Business Consultant | 4
Jiaxiang WANG | Software Engineer | 37
Jie TIAN | Sr. Project Manager | 26
Jingbin LI | Intern | 19
Joanna JI | QA Analyst | 28
John TAN | Project Manager | 24
John XIE | Assoc. Solution Architect | 34
Johnny YU | Business Analyst | 2
Johnson ZHONG | Sr. Solution Architect | 41
Joyce LIU | User Researcher | 12
Jupei LU | Intern | 19
Karthik RAMASWAMY | Sr. Solution Architect | 41
Katharina MA | Intern | 19
Ke BI | Sr. Project Manager | 26
Kent SUN | Software Engineer | 37
Kilin LEE | Sr. Software Engineer | 40
Larry SUN | Designer | 6
Lawrence HE | Sr. Software Engineer | 40
Leon REN | Software Technical Lead | 38
Link YANG | Solution Architect | 39
Lisa LI | Sr. QA Analyst | 31
Liye SHI | Sr. Data Specialist | 18
Lucy ZHENG | Software Engineer | 37
Marvin CUI | Software Engineer | 37
Mary YAN | Business Analyst | 2
Mary YUAN | Intern | 19
Matthew ELSOM | Head of Design | 8
May YANG | Sr. Software Engineer | 40
Meiyi LI | Jr. Developer | 36
Meiying LI | Jr. Developer | 36
Messi CONG | Sr. Software Engineer | 40
Mona LI | Intern | 19
Monica YANG | Assoc. Project Manager | 21
Ni LI | QA Analyst | 28
Nick WU | Sr. Software Engineer | 40
Ning LI | Software Technical Lead | 38
Oscar SHU | Developer | 35
Polina PENG | Software Tester | 30
Qi ZHANG | Jr. Developer | 36
Qingshen KONG | Jr. Developer | 36
Quintina MEI | QA Analyst | 28
Rentao XIAO | Sr. Software Engineer | 40
Renzhang PAN | Intern | 19
Ronglei HU | Intern | 19
Sandy WANG | Project Lead | 23
Shaoyu WANG | Jr. Developer | 36
Shenglin JIN | Intern | 19
Shin GAO | Software Engineer | 37
Shishuai LIU | Jr. Developer | 36
Shuai PANG | Jr. Developer | 36
Shuai ZHOU | Sr. Project Manager | 26
Simon HU | Software Technical Lead | 38
Summer ZHANG | Sr. Project Coordinator | 25
Tingchong LIU | Project Manager | 24
Tiny CHEN | Business Analyst | 2
Tom LIU | Software Engineer | 37
Tony YANG | Software Technical Lead | 38
Vicky LI | Sr. QA Analyst | 31
Vicky ZHU | Sr. Business Analyst | 3
Wenyu WANG | QA Analyst | 28
White BAI | Software Engineer | 37
Will BI | Software Technical Lead | 38
Xian TANG | Software Engineer | 37
Xiaoning GUO | Software Technical Lead | 38
Xinfeng LIU | Intern | 19
Xinning CHIA | Designer | 6
Yang CHEN | QA Analyst | 28
Yang SONG | Software Engineer | 37
Yang YANG | Data Technical Lead | 16
Yantao LIU | Software Engineer | 37
Yici ZHONG | QA Analyst | 28
Yifeng LIU | Intern | 19
Yupeng CHEN | Intern | 19
Zhaojiang PEI | Intern | 19
Zheng LI | Sr. Software Engineer | 40
Zhikang ZENG | Jr. Developer | 36
Zoi CHU | QA Analyst | 28
Zora DONG | Intern | 19
Shu JIANG | Assoc. Project Manager | 21
Hongnan GAO | Developer | 35